TO: LHRT Executive Committee

FROM: Michele Cloonan and Melanie Kimball, Co-Chairs Library History Seminar XIII

DATE: June 16, 2014

The Planning Committee met on March 11, 2014 to discuss the conference.  Prior to the meeting, the co-chairs developed a timeline of events leading up to the conference, and a draft of the call for papers.  The Committee gave input to both documents, and discussed ideas for keynote speakers. Due to the difficulty in scheduling face to face meetings, the Committee will do the bulk of its work online and via conference call or Skype.

The conference will open on Friday, July 31 and end Sunday, August 2.  Special tours of Boston area libraries will take place in the days prior to the start of the conference.

Call for Papers

The preliminary Call for Papers was finalized in March2014 and a “Save the Date” message posted to appropriate email lists such as LHRT and SHARP. The first formal Call for Papers will go out in July 2014 and will be repeated in September and October. The deadline to receive paper and panel proposals is November 1.

Website

Christina Stone, Melanie’s Graduate Student Assistant (GSA), prepared materials for the conference website and a trailer.  Her GSA ended in April, but we will have additional student help in the next academic year.  The website will go live with the Call for Papers and general information in July.  We will update the website as appropriate in the fall and spring to include information on registration, housing, travel, and so forth.

Housing

We have reserved rooms in the Simmons College Residence campus for the weekend of the conference.  For those who do not wish to stay in the dorms, there are many nearby hotels.  There will be a conference banquet on Saturday evening.  Snacks and beverages will be provided for breaks, but other meals will not be provided.  There are a wealth of restaurants near Simmons College as well as a coffee shop and cafeteria on campus.

Keynote Speakers

We plan to have two keynote speakers.  Ann Blair, Historian and Professor at Harvard University, and author of Too Much to Know: Managing Scholarly Information before the Modern Age agreed to be one of our keynote speakers.  We are in conversations with another keynote speaker but as of this writing have not confirmed that he will be available.  We are also pursuing other speakers should he give us a definite “no” answer.

Auction

We will hold an auction during the conference, as has been the custom at the last two Seminars, with proceeds going to LHRT.  Sid Berger will serve as auctioneer.  In January or February 2015 wee will send out information for those who wish to donate materials to the auction.

Committee Members

We will solicit additional members for the various committees, particularly the jury committee, later this summer.

Attachments

Attached are the preliminary call for papers, the list of Planning Committee members and their affiliations, a draft list of other committees and their members, and a timeline.

Respectfully submitted,

Melanie Kimball and Michele Cloonan, Co-Chairs

Library History Seminar XIII

Timeline for Library History Seminar XIII

Libraries: Traditions and Innovations

Simmons College

July 31-August 2, 2015

March 2014		Hold the Date notice goes out to various lists (will be repeated periodically)

March 2014-July 2014	Selection of keynote speakers

July 2014		First call for papers; Conference website goes live

September 2014	Second call for papers

October 2014		Final call for papers

November 1, 2014	Deadline for papers

Nov. 2014-Jan.2015	Jury Committee deliberation

Jan. 15-Feb. 15, 2015	Individuals and panels contacted

February-June 2015	Items for auction collected

March 2015		Preliminary conference program

May-June  2015		Finalize Conference program

July 31-Aug. 2, 2015	Conference!!!

CALL

Library History Seminar XIII:

Libraries: Traditions and Innovations

July 31 - August 2, 2015

Pre-Conference Trips, July 30-31, 2015

Graduate School of Library

& Information Science

Simmons College

Boston, MA 02115

Boston, Massachusetts, the site of the Library History Seminar XIII, provides an apt setting to explore traditions and innovations in libraries. The Boston area is home to many important library innovations in North America, including the first university library and the first large, free municipal library. At the same time, new information institutions continue to be created here, of which the Digital Public Library of America and the Digital Commonwealth of online heritage materials are two recent examples.

With Boston as the backdrop, this conference seeks to delve into the enduring and evolving aspects of libraries and librarianship. The convergence and divergence of the physical and the digital may result in opportunities and challenges that we do not yet realize. Traditionally libraries have made their collections available to defined audiences, but today it is increasingly difficult to define and delineate user communities. At the same time, so-called “disruptive technologies” in publishing are resulting in new approaches to the collection and dissemination of information. The Library History Seminar XIII will provide a lively forum for such scholarly debate.

We encourage the submission of papers that explore the notion of the library, from brick-and-mortar to digital. Topics include, but are not limited to, the history of library services and types, library architecture, the library as place, library users (digital and virtual), library communities, challenges and opportunities of cyberspace, disruptive technologies, social media and networking, pop-up libraries, online learning, and social reading.

Library History Seminar XIII

Planning Committee

Michele Cloonan, Simmons College (michele.cloonan@simmons.edu), Co-Chair

Melanie Kimball, Simmons College (melanie.kimball@simmons.edu), Co-Chair

Benjamin Abrahamse, MIT (babraham@mit.edu

Sid Berger, Peabody Essex Museum & Simmons College (sid@pem.org; sid@simmons.edu)

Tom Bolze, Yale University (thomas.bolze@yale.edu)

Beth Caroll-Horrocks, Massachusetts State Library (bcarrollhorrocks@gmail.com)

Hope Mayo, Harvard University (mayo@fas.harvard.edu)

Tom Michalak, Harvard University—retired (cruikshank1@comcast.net

Oceana Wilson, Bennington College (owilson@bennington.edu)

Kathy Wisser, Simmons College (katherine.wisser@simmons.edu)

Others

Christina Stone, Graduate Assistant (christina.stone@simmons.edu)

Bernadette Lear and Dominique Daniel, LHRT, ex officio

Library History Seminar XIII

Committees and Descriptions (Preliminary)

- Auction –  Coordinates reception of donations for auction, plans event

  - Graduate Assistant

  - Sid Berger (auctioneer)

- Financial and institutional support (sponsors) – identifies and approaches possible sponsors to donate to the seminar

  - Sid Berger

  - Tom Michalak

- Jury committee – Evaluate presentation abstracts and approve for inclusion in the Seminar

  - Tom Bolze

  - Ben Abrahamse

  - Tom Glynn

- Local arrangements – coordinates housing, trasnsportation, welcome packets, local information, and tours

  - Beth Carroll-Horrocks

- Planning Committee – oversight of planning for entire conference (see separate list of members)

- Post-conference publications – arranges for articles stemming from conference to be published in peer-reviewed venue(s); possible online “publication” of sessions

  - Melanie Kimball

- Program Committee (post acceptance) – schedules sessions, keynotes,auction,  receptions, final dinner, etc.

- Social Media/Conference trailer /Conference Website

  - Graduate Assistant

- Speakers – Identify and approach people to give keynote and plenary addresses

  - Michele Cloonan